# FY2010 Committee Planning Form

Committee Name:    Technology

Committee Chair:  Ann Gruhn and Walt Daniels

| Committee Objective | Key Tasks | Necessary Resources |
| --- | --- | --- |
| Provide oversight to foster compatible and/or integrated technology solutions that meet the needs of the Trail Conference | Participate in studies and key discussions of committees and staff units to provide the technology point of view. | Technology committee members (up to 10 hours per month) |
| Status Quo Hardware/Software /Services | Upgrade hardware as necessary. Inventory hardware and build refresh plan for existing hardware. | No known needs for 2010. (Josh—do you have better info?) 15 hours for inventory (volunteer and staff) |
|  | Software and other licensing fees | Domain names (9 at approx $11 ea.); GIS software (ESRI approx $800, Map Publisher approx $200); Possible upgrade of 3 Quickbooks licenses in 2010 (approx $200 ea.) Josh – please confirm $ and add any I don’t know about (e.g. antivirus upgrades). |
|  | Inventory software and build refresh plan | 15 hours (volunteer and staff) |
|  | Ebase programming in support of various TC functions (volunteers, trails, etc.): | 380 hours / yr; Includes: * Creating, modifying and managing Filemaker databases & database processes in response to TC needs; * Providing accurate & timely routine or special reports and data retrievals; & * Maintaining acceptable levels of data quality & integrity and an acceptable level of security for the databases. |
|  | Hardware & software services contracts | TIS - $15K; a2hosting - $2K Josh – please confirm TIS $. |
| Ongoing Web management (we averaged 300 hours per month of volunteer effort on Web activities so far this year) | Add content, update content | Contract staff (GW @ ? hrs/month + volunteers @ 250 hrs/month) Note: estimate depends on volunteer availability) |
|  | Monitor and track Google analytics | 7 hours/week (volunteer) |
|  | Web maintenance - webmaster monitors and upgrades software; minor enhancements implemented | 30 hours/week (volunteer) |
|  | Web programming : (1) back up webmaster; (2) Drupal coding for new functionality | (1) 10 hrs/mo – contractor or volunteer); (2) contracted support @ $1K / month |
| Synchronize membership information between ebase and Web site | Migrate ebase membership info to Web, establish procedure to keep it current | 60 hours (volunteer and staff) |
| Migrate Web site to Drupal 6 | Redo theming , create new site and test | 100 hours (webmaster) and 20 hours Drupal programmer (volunteer or contractor, $0 - $2000 cost range ) |
| Identify CRM tool to use and create budget for implementing as part of 2011-12 plan. | Determine requirements, priorities and responsibilities, select tool and build implementation plan | 100 hours (volunteer and staff) |
| Accomplish technology components of other strategic initiatives | Volunteer: Web system for volunteer records implemented by summer 2010 | Dependent on synchronized ebase membership project. Volunteer hours / costs to be determined. |
|  | Trails: Add 3-5 hikes per month | 10 hours / hike volunteer time |
|  | Marketing: Integrate social networking tools and online videos | Effort depends on availability of volunteers (a guess would be approx. 10 hours/week for each social networking tool); possible use of paid or unpaid interns (summer and school year) |
|  | Marketing: apply guidelines across all platforms | Volunteer time to update Web content – depends on how extensive changes are |
|  | Fund raising: develop budget and plan for data management and ecommerce supporting fundraising plan by 2012 | Technology committee involvement in planning |
| Work with staff to streamline office processing by leveraging technology | Examples: investigate whether Ubercart can assume most of store processing function; review use of QuickBooks to determine if we have outgrown the version we are using. | Technology committee volunteers & staff |
| Identify tool for bulk emailing to replace emailnow, capwiz and email from the Web site | Gather requirements, select tool and build implementation plan and budget for 2011-12 | Unless this activity is already in plan some place else? |

## Notes:

- It is difficult to assess the status quo hardware, software and services budget as this is not centrally managed.  An inventory and refresh plan will be helpful in future years, hence they are included in the efforts listed above.

- In future budget planning, it would be helpful if technology investments and expenses planned by other budget units were linked to the technology plan. We took guesses here from what was referenced in the strategic framework (June22, 2009) document and the needs we are aware of.

- This table is in priority order except that the strategic initiatives have not been prioritized.

- We don’t have the actuals for many of the $ numbers.  Josh, please provide details as available.

- Rough summary totals:  volunteer hours: 900 minimum, possibly up to 2X that; staff hours: 60 minimum plus whatever Georgette and Catherine are budgeted for (? for Web content and 380 hours for ebase support);  dollars: $30K minimum, another $9K desirable.

- Several projects resulting from strategic initiatives have not been defined well enough yet to include technology budget estimates.

- Please note:  I didn’t see Georgette in the staffing file that Josh sent.  Are contractors covered elsewhere?

- Last updated 9/11/2009 by Ann.

# Footnotes

Please see SMART_Objectives.pdf for more information about creating useful objectives.

Identify key tasks that must be accomplished to achieve the objective.  Include task timeframe if appropriate.

Include staff hours, volunteer resources and material costs required to accomplish the objectives